## Sheet1
Projekt Plan for Building a CI/CD Pipeline, with quarterly and yearly goals attached
Link to: trello board: https://trello.com/b/yTQlTqPd/project-building-a-ci-cd-pipeline
Week | Back End | Front end | Estimated delivery | Estimation of time
2021-01-17 | instantiate project on GitHub | - | Set up code repositoy and include starter files | 1 hour
2021-01-24 | Create Continuous Integration pipeline on Github | - | Set up Makefile, pylint, pytest | 4 hours
2021-01-31 | Test build pipeline | - | Set up Github actions for buiild pipeline | 4 hours
2021-02-07 |  | Configure the flask app | python script that gets user input and return a score based on the ML model | 4 hours
2021-02-14 |  | Test the app on local host | Test results will be shortly describe and added as part of the documentation | 1 hours
2021-02-21 | Set up Continuous Delivery | - | Create an Azure pipelines that deploys an Azure web app | 4 hours
2021-02-28 | Test continuous delivery | - | Test report | 8 hours
2021-03-07 | Documentation | - | A README.md file | 2 hours
2021-03-14 | A video guideline explaining and documenting the project | - | Video materiale for 1-5 mins | 8 hours
Top 3 Quaterly Goals | Order prioritized Fatures |  | Proposed Difficulty 1-3 (1 easy and 3 is hard)
Expand the flask API to serve an pre-trained NLP models, like BERT |  |  | 1
Write predictions to a database |  |  | 2
Set up central logging repository that persists logs from multiple web apps |  |  | 1
Top 3 Yearly Goals
Deploy a web app to akubernetes cluster using AKS with a CI/CD pipeline |  |  | 3
Build a front-end using Angular to serve the predictions from the web app |  |  | 2
Develop the web app to also be able to serve a Mleap model object when the model is trained with spark |  |  | 3
Formulas:
Week = [Week, row above]+7